## Slide 1
Dissemination plan - draft
presentation
dr Danijela Zubac, dr Bojan Prlinčević,
Applied studies professors
ASSKM
"Funded by the European Union. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union. Neither the European Union nor the granting authority can be."
KICK-OFF MEETING, BELGRADE, 23-25 JAN, 2024
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813

## Slide 2: Introduction
Project summary
The overall goal of the WBNET project is to introduce joint short study programs in the higher education institutions (HEIs) of the Western Balkans (WB) through the establishment of the Centres for Short Study Programs.
Dissemination objectives
The main objectives of dissemination plan are to ensure that the project's results are effectively communicated to the relevant stakeholders and that the project outcomes are utilized to their maximum potential.
The primary goal of project dissemination is to engage all relevant stakeholders and provide an updated information on project results.
Making accessible tangible project products (project outputs);
Raising awareness and extend the impacts (project outcomes).
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813

## Slide 3: Target audience & communication channels
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
The dissemination will be organized on different levels (department, institutional, local, regional, national, and international), aimed at different target groups (academic staff, current and prospective students, universities in partner countries, industrial and business communities) and carried out during and post the project.
Main target groups aimed to be tackled with dissemination activities are:
Students of participating WB HEIs,
Academic staff of participating WB HEIs,
Universities in surroundings,
Industrial and business institutions in partner countries including techno parks, business incubators, foundations for the development of innovative businesses and start-ups, and similar,
Individuals willing to up-skill themselves.

## Slide 4: Dissemination activities
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
Dissemination activities will be implemented in line with the Dissemination Plan developed and approved during the Kick-off meeting. Dissemination work plan will be with the list of specific project outcomes and outputs to be disseminated, dissemination levels, list of tools and channels linked to specific target groups and particular time period along with the list of indicators and evidences.
Dissemination of the project will encompass both ongoing activities during the whole life of the project (such as project website population, continuous posting in project social media groups, publication of announcement and news on partners’ websites and social media, project presentation at events of different levels, biannual newsletters etc.) and dedicated activities and events.
The activities will be led by Dissemination Board composed of the representative from each HEI, while associated partners will help. Its main task is to guarantee ongoing dissemination activities.

## Slide 5
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
Table 1: Dissemination activities at different phases of project cycle
Project cycle phase | Dissemination activity
Project preparation phase | drafting the dissemination plan, definition of the expected impact and deliverables, identification of target audience & communication channels.
During the project | contacting relevant media e.g. at local or regional level, conducting regular activities such as training, study visits, assessing the impact on target groups, involving other stakeholders in view of transferring results to end users/new areas/policies, evaluating the dissemination in the mid-term period.
Final reporting period | uploading the final project results and an update of the project description on the Erasmus+ Project Results Platform
After the project | continuing further dissemination, developing ideas for future cooperation, evaluating achievements and impact, contacting relevant media, contacting policy-makers if relevant, cooperating with the European Commission by providing useful inputs to its dissemination and exploitation efforts.

## Slide 6: Dissemination tools
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
Dissemination tools and materials will be developed to provide concrete support to dissemination activities. The plan also outlines a clear methodology for utilizing the materials and tools. This ensures uniform usage among all partners, fostering a consistent and cohesive message.
From the very beginning of the project each HEI will establish on its website notification about the project. Moreover, project website will be lunched.
Logo of the project will be developed and used for communication through all media.
Dissemination is going to be through all the media (TV, radio, internet, social-networks).

## Slide 7: Dissemination tools
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
Promo material (T-Shirts, notebooks, flyers, USB, pens) shall be provided for all HEIs and due the fact that all HEIs have excellent relations with local and state TV program producers, this is going to be a project that people talk about
The latter will be a series of information sessions held at HEIs in partner countries with the main aim to inform target groups and wide public about the project and its results, and Final Conference.
The current project will also become a good basis for joint scientific and methodological work with its results published in national and international prints.

## Slide 8: Dissemination tasks
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
Task No | Task Name | Description | Participants
T7.1 | Developing Dissemination and Exploitation Plan | DB will work according to Project Management Plan and create Dissemination Plan with strong timeline scheduling. Dissemination is going to be strong support for each activity that consortium conduct with stakeholders. | All beneficiaries
T7.2 | Developing website and conducting | Development of Online Platform (website) starts immediately after received positive answer from the EU Commission. Online Platform will be created for the project as an important and ongoing communication hub and as a tool for preparation, development, quality, management, sustainability and dissemination of project outcomes. The Online Platform will crucially contain, in addition to in-detail project description, goals, partners, etc. all training, teaching and learning materials, developed by partners. All the materials will be available for free download during and post the project. AASKM and ATUSS will create website | All beneficiaries

## Slide 9: Dissemination tasks
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
T7.3 | Development of promo material | Logo of the project will be developed immediately after signing Grant Agreement. In order not to waste time, Working Group that ATUSS leads will develop logo, prepare promo kit I. 10 different promo-kits are going to be developed. | All beneficiaries
T7.4 | Promotion on media and social networks | All media that can be reached will be used. Websites of partners, stakeholders, social media, TV stations, radio etc. | All beneficiaries
T7.5 | Promotion on live events | All events will be covered with photos, video-clipping and TV stations are going to be called to make the coverage | All beneficiaries
T7.6 | Monography of the project | The Monography of the project activities and results is going to be prepared and published. It is going to be in colour, 100 pieces. It will be distributed on Final Conference. | All beneficiaries
Task No | Task Name | Description | Participants

## Slide 10: Dissemination deliverables
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
Deliverable No | Deliverable name | Due date (month number) | Description (format and language)
D7.1 | Dissemination plan | M3 | electronic, EN
D7.2 | Website of the project launched and sustain | M3 | electronic, EN
D7.3 | Promo material for the project promotion | M2 | electronic, printed, EN, Serbian, Bosnian
D7.4 | Media content and announcements through social media of HEIs and economy partners | M36 | electronic, EN, Serbian, Bosnian
D7.5 | Project promotion on live events organised during the project life | M32, M36 | electronic, EN
D7.6 | Monography | M31 | electronic, EN, Serbian, Bosnian

## Slide 11: Exploitation
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
The primary goal of the exploitation plan is to continue supporting both the tangible and intangible outcomes of the main project, translating research and development efforts into practical solutions that benefit society, industry, and the economy. The following key points are essential for accomplishing this objective:
1. Joint short study programs are attractive, up-to-date and conform to quality standards;
2. Centers for short study programs are operational and sustainable, signing cooperation agreements, based on each economy partner needs;
3. During round tables and Interim and Final conference the wider group of stakeholders and decision makers are invited;
4. Monography of the project is delivered on the Final event to all stakeholders in order to provide project sustainability.

## Slide 12
Network of centers for regional short study programs in the countries of the Western Balkans
Call: ERASMUS-EDU-2023-CBHE
Project number: 101128813
Thank you for your attention!